## Sheet1
[6 empty] | CONCEPT | [6 empty] | DEVELOPMENT | [6 empty] | FINALIZE | [6 empty] | POST
[6 empty] | July | [6 empty] | August
Department | Week | Task | Priority | Deadline | Status | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Project Management | WEEK 1 | Assemble team contact list | EXTREMELY HIGH | 2020-07-26 | COMPLETED | bar: July 25 to July 26
|  | Schedule weekly meetings | HIGH | 2020-07-26 | COMPLETED | bar: July 25 to July 26
|  | Prepare a summary of action items | HIGH | 2020-07-26 | COMPLETED | bar: July 25 to July 26
|  | Create a project timeline | HIGH | 2020-08-01 | COMPLETED | bar: July 25 to July 31
| WEEK 2 | Request status updates from team members | HIGH | 2020-08-06 | COMPLETED | bar: August 1 to August 6
|  | Review schedule for deliverables. Adjust as needed | HIGH | 2020-08-04 | COMPLETED | bar: August 1 to August 4
|  | Update summary of action items | HIGH | 2020-08-04 | COMPLETED | bar: August 1 to August 4
|  | Identify potential risks and mitigation | EXTREMELY HIGH | 2020-08-11 | ONGOING | bar: August 1 to August 11
| WEEK 3 | Request status updates from team members | HIGH | 2020-08-11 | ONGOING | bar: August 8 to August 11
|  | Update summary of action items | HIGH | 2020-08-11 | COMPLETED | bar: August 8 to August 11
|  | Evaluate team performance (yours included) | HIGH | 2020-08-18 | NOT STARTED | bar: August 15 to August 17
Writing | WEEK 1 | Create broad outline of story | HIGH | 2020-07-31 | COMPLETED | bar: July 25 to July 31
|  | W/T establish story beats for concept art | EXTREMELY HIGH | 2020-07-31 | COMPLETED | bar: July 25 to August 4
|  | W/T come up with attraction name | LOW | 2020-08-11 | COMPLETED | bar: July 25 to August 11
| WEEK 2 | Develop logline & synopsis | HIGH | 2020-08-04 | COMPLETED | bar: August 1 to August 4
|  | Start writing treatment | HIGH | 2020-08-04 | COMPLETED | bar: August 1 to August 4
| WEEK 3 | Finalize treatment | EXTREMELY HIGH | 2020-08-04 | COMPLETED | bar: August 8 to August 11
|  | W/T finalize guest experience boards | EXTREMELY HIGH | 2020-08-04 | COMPLETED | bar: August 8 to August 11
|  | Flesh out the deck, including final edits | HIGH | 2020-08-04 | ONGOING | bar: August 8 to August 11
Graphic Design | WEEK 1 | Decide on software for deck | LOW | 2020-07-31 | COMPLETED | bar: July 25 to July 31
|  | Distinguish tone of project | HIGH | 2020-07-31 | COMPLETED | bar: July 25 to July 31
|  | Begin rough layout of pages | MEDIUM | 2020-08-07 | COMPLETED | bar: July 25 to August 7
| WEEK 2 | Work with PM to receive final creative materials | HIGH | 2020-08-07 | ONGOING | bar: August 1 to August 13
|  | Work with Writer to choose segments of treatment | HIGH | 2020-08-06 | COMPLETED | bar: August 1 to August 6
|  | Review W/T the quality of the messaging in deck | HIGH | 2020-08-06 | ONGOING | bar: August 1 to August 11
| WEEK 3 | Complete Blue Sky pitch deck | EXTREMELY HIGH | 2020-08-15 | ONGOING | bar: August 8 to August 14
|  | Review pitch deck with team for presenting | EXTREMELY HIGH | 2020-08-13 | ONGOING | bar: August 8 to August 13
|  | Check in with illustrators if need help | HIGH | 2020-08-11 | ONGOING | bar: August 8 to August 11
Illustration | WEEK 1 | Create quick ideation sketches | MEDIUM | 2020-07-31 | COMPLETED | bar: July 25 to August 2
|  | Assemble preliminary moodboards | MEDIUM | 2020-07-31 | COMPLETED | bar: July 25 to July 31
|  | Create research image libraries | LOW | 2020-07-31 | COMPLETED | bar: July 25 to July 31
|  | Decide what story points need artwork | HIGH | 2020-07-31 | COMPLETED | bar: July 25 to August 2
|  | Decide what type of/how much art for deck | HIGH | 2020-08-06 | COMPLETED | bar: July 25 to August 2
| WEEK 2 | Make any necessary modifications to artwork | HIGH | 2020-08-07 | ONGOING | bar: August 1 to August 11
|  | Artworks at 50%, Diagram at 50% | HIGH | 2020-08-07 | COMPLETED | bar: August 1 to August 7
| WEEK 3 | Artworks at 100%, Diagram at 100% | EXTREMELY HIGH | 2020-08-11 | ONGOING | bar: August 8 to August 11
|  | Help fellow Illustrator where needed | EXTREMELY HIGH | 2020-08-11 | ONGOING | bar: August 8 to August 11
|  | Work with GD to put artwork & diagrams into deck | EXTREMELY HIGH | 2020-08-14 | ONGOING | bar: August 8 to August 14